## Gantt
NBA GAME OUTCOME PREDICTION | [6 empty] | Group name : |  |  | Tugay Balatlı - Ata Berk Çakır
[5 empty] | Project start date: | [5 empty] | 2021-10-12 | [23 empty] | 1
 | time axis 2021-10-11 to 2022-10-03
| TASK NAME | START DATE | END DATE | WEEKS | W42 | W43 | W44 | W45 | W46 | W47 | W48 | W49 | W50 | W51 | W52 | W53 | W2 | W3 | W4 | W5 | W6 | W7 | W8 | W9 | W10 | W11 | W12 | W13 | W14 | W15 | W16 | W17 | W18 | W19 | W20 | W21 | W22 | W23 | W24 | W25 | W26 | W27 | W28 | W29 | W30 | W31 | W32 | W33 | W34 | W35 | W36 | W37 | W38 | W39 | W40 | W41
| Literature Review (Tugay Balatlı - Ata Berk Çakır) | 2021-10-12 | 2021-11-09 | 5
| Problem Definition (Tugay Balatlı - Ata Berk Çakır) | 2021-10-12 | 2021-10-17 | 1
| Solution Proposal (Tugay Balatlı - Ata Berk Çakır) | 2021-10-18 | 2021-10-20 | 1
| Data Collection (Tugay Balatlı - Ata Berk Çakır) | 2021-10-18 | 2021-10-27 | 2
| Data Preprocessing (Tugay Balatlı - Ata Berk Çakır) | 2021-10-25 | 2021-11-09 | 3
| Logistic Resgression Implementation (Ata Berk Çakır) | 2021-11-15 | 2021-12-05 | 3
| SVM Implementation (Tugay Balatlı - Ata Berk Çakır) | 2021-11-22 | 2021-12-10 | 3
| Decision Tree Implementation (Tugay Balatlı) | 2021-11-29 | 2021-12-19 | 3
| Performance Test (Tugay Balatlı - Ata Berk Çakır) | 2021-11-29 | 2021-12-20 | 4
| Hyperparameter Tuning (Tugay Balatlı - Ata Berk Çakır) | 2021-12-20 | 2021-12-27 | 2
| Reporting Results (Tugay Balatlı - Ata Berk Çakır) | 2021-12-20 | 2021-12-28 | 2

## Readme
Getting started guide
| • | Enter the [Project Name], [Project Manager], and [Company Name].
| • | Enter the Project Start Date (M3). This will automatically update the dates shown in the timeline.
| • | Add details of your tasks, such as TASK ID (optional), TASK NAME, START DATE, and END DATE.
| • | To change the range of weeks displayed in the timeline area, just slide the scroll bar.
|  |  | Note: | Please do not change the dates/weeks in the timeline manually.
| • | To add more tasks:
|  |  | Step 1: | Copy a single row or several rows at once.
|  |  | Step 2: | Select the row after the last task (Row 23), then right-click and select Paste or Insert Copied Cells (recommended).
Note: If you want to insert the copied cells between tasks, just select any task's row, then right-click and select Insert Copied Cells.
| • | To add more weeks in the timeline:
|  |  | Step 1: | Copy one column (e.g. BF) or several columns at once.
|  |  | Step 2: | Select the column after the last week (BG), then right-click and select Insert Copied Cells.
The WEEKS column
| • | The WEEKS column gives you the info about the total week between the START DATE and END DATE.
| • | The values in this column do not affect the bars.